## Sheet1
Task Name | Duration | Start | Finish
Requirements Phase
Research of technologies | 4 days | 2014-10-18 | 2014-10-22
Requirements Analysis | 3 days | 2014-10-20 | 2014-10-22
Post jailbreak review | 8 days | 2014-02-09 | 2014-02-16
Design Phase
Design proposal | 7 days | 2014-10-20 | 2014-10-26
Present design to client | 1 day | 2014-10-27 | 2014-10-27
Revise Design | 3 days | 2014-10-27 | 2014-10-30
post jailbreak re-design | 11 days | 2015-02-14 | 2015-02-24
Development Phase
Alpha version | 66 days | 2014-11-01 | 2014-01-05
Beta version | 25 days | 2015-01-09 | 2015-02-02
Jailbreak | 2 days | 2015-02-07 | 2015-02-08
Production version | 25 days | 2015-02-24 | 2015-05-18
COMX | 2 days | 2015-05-28 | 2015-05-29
Testing Phase
Alpha testing | 70 days | 2014-11-01 | 2015-01-09
Beta testing | 29 days | 2015-01-09 | 2015-02-06
Production testing | 93 days | 2015-02-24 | 2015-05-27
Efficiency testing | 15 days | 2015-03-23 | 2015-04-06
UAT testing | 12 days | 2015-04-06 | 2015-04-17